## Product planning
Tasks | Winter 2020 |  |  |  | Summer 2020 |  |  |  | Fall 2020 |  |  |  | Winter 2021 |  |  |  | Summer 2021 |  |  |  | Fall 2021
| Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sep. | Oct. | Nov. | Dec.
Literature Review (Ongoing...)
Dataset Selection
Benchmark Selection
Benchmark Implementation
Preliminary Analysis
Deep Learning Implemention
Final Analysis
Proposal Writing
Proposal Presentation
Thesis Writing
Thesis Defense